## Slide 1: Final Year Project: Week 13 of 20
Robust Optimisation of Composite Panels
Marij Qureshi 16th Jan 2020

## Slide 2: Progress
Isight Automation – 1 week cut-off
  Couldn’t get it to work – part of research
Main effort: Report synthesis and write-up – good progress
Reliable Design - completed
Robust + Reliable Design – completed
Now all structural design work completed, little more work on algorithm comparison needed

## Slide 3: Optimal Design Comparison
Algorithm: NSGA2 (20 generations, 20 points per generation)
  Slow, but most reliable for finding global optimum
  Local optima at each side of design space

## Slide 4: Optimal Design Comparison

## Slide 5: Problems
Large variations in response
  Fixed 1mm standard deviation geometry tolerances
  What is realistic for composite manufacture?
  Reducing this makes results look more like distinct peaks – deterministic always best
  Would reducing design space help?
Hybrid design dominates robust
Reliable design dominates deterministic
  Indicates optimisation weighting wrong

## Slide 6: Optimisation Problems
Deterministic
Constraints:
Mass < Baseline
Buckle Load > Baseline
Objectives:
Minimise Mass
Maximise Buckle Load
Robust
Constraints:
Mass < Baseline
Buckle Load > Baseline
Objectives:
Minimise Mass
Maximise Buckle Load
Minimise SD Mass
Minimise SD Buckle Load
Reliable
Constraints:
Mass < Baseline
Buckle Load > Baseline
Failure < 0.1% ?
Objectives:
Minimise Mass
Maximise Buckle Load
Minimise Failure %
Robust + Reliable
Constraints:
Mass < Baseline
Buckle Load > Baseline
Objectives:
Minimise Mass
Maximise Buckle Load
Minimise SD Mass
Minimise SD Buckle Load
Minimise Failure %

## Slide 7: Next steps
Exam week coming up – divert more attention there
Continue work on algorithm explanatory problems
Continue work on write-up

## Slide 8: Progress
Case 1: Plate with hole
Case 2: Deterministic mono-string
Case 3: Robust mono-string
Workflow set-up and learning
Program efficiency + validation
Results validation + analysis
Final Report Work
Main Objectives
Auxiliary Objectives
Wks 1-3
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Month | Jan |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  | 
Wks 4-9
Wks 10-15
Wks 17-19

## Slide 9: Mono-string: Problem
  Design Variables
  Geometry:
  Constraints (mm)
  Objectives
  Maximise 1st Eigenvalue
  Minimise semi-length mass
Notes: Post-buckling reliability design (vary lay-up)
Chapter 7: Robust Multilevel Design Optimization of Composite Panels
Robust and Reliability-Based Design Optimization of a Composite Floor Beam